## Home
Hi!
This spreadsheet is created with top priority only to keep track of scenarios, bugs and tasks.

The spreadsheet has 4 subsheets as follows,
1.Home
2.Scenario
3.Bug
4.Task

If you are planning to ignore this sheet, then I guess you are also planning to turn down the whole project and walk into hell.

I request each of you to update every scenario, every bug and every task performed in this sheet with all due respect.

Thanks.

## Scenario
Scenario id	Problem Statement					Author	Date	Solution	Solved by	Solved on
Scenario001

## Bug
Bug id	Bug Description					Bug Founder	Detected on	Fixer	Fixed on	Defect Reason	Screenshots, If any	Status	Acknowledged By
Bug001	"No Results Fetched try again" message partly hides behind the FOOTER					Karthik	12-Apr-12	senthil	2012may01	simple functionality so less priority		Open

Bug002	Search key - "b harper", "b" hits results from TITLES and "harper" from FILTER "Publishers". The link displayed above the search result says "You also have results fetched based on the filters - 'harper' in books_lists" whereas it should say "'harper' in publishers"					Karthik	12-Apr-12	senthil	2012may01	I wont say it is completely fixed because, for “b” you wont get a match since sphinx search for single letters are not enabled for reasons we will discuss.		Open

Bug003	Don't display "books_lists" to users, instead do show them simply "books"					Karthik	12-Apr-12	senthil	2012may01	fixed in all the html.		Open

Bug004	Click "Visit Shop" under LOCAL SHOPS tab and navigate to the local shops specific page. Select an area from the drop down in the "Shop Details" page, "Shop Location" child tab opens up but the drop down in there is not displaying the area i chose from the previous tab.					Karthik	12-Apr-12	senthil		not fixed. In fact not handled yet.		Open

Bug005	Local shops grid has to be dealt in a different way. Find the value in the "door_delivery" field and if it says "y", show the shipping cost and time. If it says "n", simply display "not available" under shipping					Karthik	12-Apr-12	senthil		It will dealt by vijay in Html		Open

Bug006	Display "View All Local Shops" under LOCAL SHOPS tab, only if the user selects any area from the drop down else don't show that message and link					Karthik	12-Apr-12	senthil	2012may01	there is no reason		Open

Bug007	Compare action should be invoked, even if the user clicks the product name. Right now it leads to an exception page					Karthik	12-Apr-12	senthil	2012may01	Not only the product_name, product_image also if clicked will take you to specific page.		Open

Bug008	Don't display the miscellaneous features in the generic page. It should be displayed only under the specifications tab and that too in a proper way					Karthik	12-Apr-12	senthil	2012may01	listen to yourself!!!		Open

Bug009	"Linkf5MobilesLists", "Linkf6MobilesLists",... etc. errors still exists					Karthik	12-Apr-12	Karthik	13-Apr-12	DB error. Values should have "F" instead of "f"		Open

Bug010	Mobiles search is still not proper. Filters are not properly organized. Miscellaneous should not come in filters. Assorteds are not properly loaded into the assorteds table					Karthik	12-Apr-12	senthil	2012may01	I think its ok now.		Open

Bug011	search for "y vga". You will get an exception. After that go back to previous page, you will get exception related to session that session does not exist					Vijay	12-Apr-12	senthil		I dont know about that error but right now, linkf11mobileslists caused an error, assigning this to K		Open

Bug012	You have disabled search for articles such as a, an , the. But a and the are keywords and there will be search results for the same					Vijay	12-Apr-12	senthil	2012may01	Finalized to remove articles if in group and do not remove if alone.		Open

Bug013	Filters for mobiles is not proper which you have acknowledged. Also, while displaying features too, you just display from DB along with $,#,% etc					Vijay	12-Apr-12	Karthik	13-Apr-12	Data error. AWK validated the mobile data now.		Open

Bug014	search for "y 2mp".in "operating system versions" filter, you can find two entries for Gingerbread. why?					Vijay	12-Apr-12	senthil		Still this error is there, we need to fix this by doing a change in the DB, discussion required.		Open

Bug015	when i search for "2mp", i dont get any results. But 2MP is part of primary camera which is part of filter. so search is enabled for it. still no results for the same. But if i search for "y 2mp", i get results in mobile_lists where in it displays all mobiles with "y" and 2mp in secondary camera.					Vijay	12-Apr-12			I dont know about that error but right now, linkf11mobileslists caused an error, assigning this to K		Open

Bug016	No search results for "motorola", though it is available in part1 [local_chennai_tambaram_thangapandi_products].					Vijay	12-Apr-12	Karthik	13-Apr-12	Data error. Validated the Saholic mobiles wrt part2 DB.		Fixed	Vijay

Bug017	Select Mobile OS version in the filter. Search tree shows the respective Version Name. Expected -> OS Version should be displayed in the search tree.					Karthik	13-Apr-12	senthil	2012may01	I think its pretty much ok now since no versoin number is displayed		Open

Bug018	Colors should not be a part of the regular filters.					Karthik	13-Apr-12	senthil	2012may01	removed it		Open

Bug019	search key – nokia. Choose "black" from the filters "COLOR". Look at the search tree built.					Karthik	13-Apr-12	senthil	2012may01	color removed!!!!!!!!		Open

Bug020	Message displayed under LOCAL SHOPS grid is not proper.					Karthik	13-Apr-12	senthil	2012may01	Then change it!!		Open

Bug021	When "View All Local Shops" link is clicked, remove the areas drop down.					Karthik	13-Apr-12	senthil	2012may01	I think its not applicable right now since the area select box is static from the start		Open

Bug022	Display filters, only when there is a value available.					Karthik	13-Apr-12	senthil	2012may01	Only in mobile_os version there is a problem whcih was mentioned before. We need to discuss.		Open

Bug023	when I search for “y vga”,i get this mysql excception: “Mysql2::Error: Unknown column 'secondary_camera_id' in 'where clause': SELECT mobiles_list_id FROM `link_f11_mobiles_lists` WHERE (secondary_camera_id IN (2) AND mobiles_list_id IN (2100000000000,2100000000006,2100000000011,2100000000015,2100000000017,2100000000020,2100000000025,2100000000030,2100000000033,2100000000036,2100000000037,2100000000039,2100000000042,2100000000046,2100000000047,2100000000014,2100000000044,2100000000045,2100000000048))”. It iis link_f10_mobiles_lists table.					Vijay	13-Apr-12	senthil	2012may01	This is becuase, secondary_camera is link_f10, data is coming in as link_f11. Assinging to K.		Open

Bug024	When I search for “8mp”, no results are fetched. If I search for “8 mp”, I get two results. One with primary camera as “8 mp” and another with “5 mp”					Vijay	13-Apr-12	senthil	2012may01	Not fixed. Right now you will get all the results that matches with 8 mp and it will be expected to display 8 mp as the first result. It is not implemented yet, its a little tricky.		Open

Bug025	“No results fetched.Try again!” page should be a new one. Right now, this error page is displayed in home page.					Vijay	13-Apr-12	senthil	2012may01	ok		Open

Bug026	a) if I search for “what brown”, search results are displayed for “what” and though there are no results for “brown”, search reults say “what brown” b) If I search for “hachette”,there should be results displayed for publisher with names “Hachette Book Publishing India” and “Hachette India Children's Books”. But only “Hachette Book Publishing India” is displayed. c) Also if I search for “Hachette India Children's Books”, then I get an error page that I am searching for special characters. d)Also if I search for “Hachette India Children”, then search results are displayed for “india”,”children” etc.but preference should be given to “Hachette India Children” publisher as it has more relevance. e) kaui hart hemmings. Little brown					Vijay	13-Apr-12					Open

Bug027	execute this query: SELECT *FROM `books_f7_publishers` WHERE publisher LIKE "h%". In this “Harper collins” is in different names, though they refer to the same publisher. So cant we make it the same.Also, there is a name “HODDER”, which should be in smaller case. This issue will be there for all filters.					Vijay	13-Apr-12					Open

Bug028	after loading dat file for a vendor, it is not possible to load data again for the same category as well as for a different category.					Vijay	13-Apr-12	senthil	2012may01	Rake tasks will be written for that.		Open

Bug029	for this isbn,9788190453028,9788179921623,9788179921623,9788121924986,9780143099703, we are getting this error:”The availability value from part-1 is not present in part-2”. But as of now, it is not possible to track the vendor in which this error is coming.					Vijay	13-Apr-12	senthil	2012may01	We have to take this seriously.		Open

Bug030	Search for smartphone. No results. Search for smart phone.results will be displayed. SUGGESTED CHANGE In part 2: type should be collected as “Android smartphone,smartphone,android phone”					Vijay	13-Apr-12	senthil	2012may01	Assigned to K		Open

Bug031	Colors need to be split in to two and inserted into proper filter tables.					Vijay	13-Apr-12	senthil	2012may01	I think K fixed it.		Open

Bug032	search for “android os v2.”, only 1 result is displayed. But there are 11 mobiles matching that criteria. Also search for “android”, 11 results will be displayed. According to DB, there are 11 mobiles matching android and gingerbread. But in filters, you can find that there are 10 results matching gingerbread.					Vijay	13-Apr-12	senthil	2012may01	fixed.		Open

Bug033	search for “tft,256k colors”,15 results will be displayed. As per DB, there are only 3 results for that search key. Likewise, searching any key in mobiles_f6_mobiles_lists table is getching wrong results. Search for “s-lcd capacitive touchscreen”, an error is thrown.					Vijay	13-Apr-12	senthil	2012may01	fixed in all the html.		Open

Bug034	fix data error in mobiles_f7_internal_storages					Vijay	13-Apr-12	senthil	2012may01	Assinged to K		Open

Bug035	while searching for “microsd”, we get 14 results. But in db there are 17 results.					Vijay	13-Apr-12	senthil	2012may01	I got 2 microsd values, have to fix it by allowing unique filter keys in filters_collections.		Open

Bug036	for card slot, if the value is NO, then data should be N.A.it applies for all cases.					Vijay	13-Apr-12	senthil	2012may01	Assigned to K and V		Open

Bug037	Double links for filters					Karthik	1-May-12	senthil	2012may02	The no of times the filter matched is taken, "uniq" fixed it
Bug038	Displaying nothing sometimes

Bug038	Displaying nothing sometimes					Karthik	1-May-12	senthil	2012may02	@books.paginate might be a cause

Bug039	Paperback has 132 in link_books_bindings but displays only 88					Karthik	1-May-12	senthil	2012may02	only part-1 search is enabled, so 88

Bug040	Filter - tree view- pagination error					Vijay	1-May-12	senthil	2012may02	a empty [] exception was not handled

Bug041	view doesnt exist					Karthik	1-May-12

Bug042	Limit 10 OFFSET 0					Karthik	1-May-12

Bug043	Keyword - "The sense of an ending" - expected result: Specific					Karthik	1-May-12	senthil	2012may02	literal_search_key used in surface_search, and unarticled_search_key used in other searches

## Task
Task ID	Task Author	Task description	To be done before	Completed Task?	Pending Task?	Reason for missing out	Last date
Task001

## Sheet5
Bug039	Paperback has 132 in link_books_bindings but displays only 88					Karthik	01/05/12	senthil	2012may02	only part-1 search is enabled, so 88